|  |  |  |  |
| --- | --- | --- | --- |
| **Tasks** | **Duration**  **(Days)** | **predecessors** | **Lead/lags** |
| **Management & Finance** | 15 Days | - |  |
| **Development** | 45 Days | Management & Finance | Lag 5 Days |
| **Marketing** | 35 Days | Management & Finance / Development | Lead 20 Days |
| **Public Relation** | 20 Days | Management & Finance / Development / **Marketing** | Lead 10 Days |

**Assuming The relation between all of the tasks is Finish to start (FS):**

|  |  |  |
| --- | --- | --- |
| Day 1 | 15 DAYS | Day 14 |
| Management & Finance | | |
| Day 2 | 1 Day | Day 15 |

|  |  |  |
| --- | --- | --- |
| Day 14 | 45  DAYS | Day 57 |
| **Development** | | |
| Day 17 | 2 Days | Day 63 |

|  |  |  |
| --- | --- | --- |
| Day 57 | 35  DAYS | Day 90 |
| **Marketing** | | |
| Day 65 | 5 Days | Day 100 |

|  |  |  |
| --- | --- | --- |
| Day 90 | 20  DAYS | Day 110 |
| **Public Relation** | | |
| Day 95 | 0 Days | Day 115 |